## Sheet1
Sprints | Task | Time Period | Members |  | Date Start | Date End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
Sprint 1 |  |  |  |  | 2020-11-22 | 2020-11-29
| Creation of Project Plan | 5 days | Tom |  | 2020-11-22 | 2020-11-26 | bar: 1 to 4
| Plan Tasks | 2 days | Tom |  | 2020-11-22 | 2020-11-23 | bar: 1 to 2
| Planning Underlying Code | 3 days | Mohammed, Joshua |  | 2020-11-22 | 2020-11-24 | bar: 1 to 3
| Creation of webpages | 5 days | Abdullah |  | 2020-11-22 | 2020-11-26 | bar: 1 to 5
| - Creating Login System | 2 days | Abdullah |  | 2020-11-22 | 2020-11-23 | bar: 1 to 2
| - Creating JSP Webpages. | 3 days | Abdullah |  | 2020-11-24 | 2020-11-26 | bar: 3 to 5
| Creation and Connection of Database | 8 days | Yonis |  | 2020-11-22 | 2020-11-29 | bar: 1 to 8
| - Setting up Database | 1 day | Yonis |  | 2020-11-22 | 2020-11-22 | bar: 1
| - Creating Connections | 2 days | Yonis |  | 2020-11-23 | 2020-11-24 | bar: 2 to 3
| - Creating Tables | 1 day | Yonis |  | 2020-11-25 | 2020-11-25 | bar: 4
| - Creating Sample Data and Applying to Tables in SQL | 4 days | Yonis |  | 2020-11-26 | 2020-11-29 | bar: 5 to 8
| Implementing Underlying Code | 6 days | Mohammed, Joshua |  | 2020-11-24 | 2020-11-29 | bar: 3 to 8
| Connecting Webpages Together | 2 days | Abdullah |  | 2020-11-27 | 2020-11-28 | bar: 6 to 7
| Update Task Delivery Form | 8 days | Joshua |  | 2020-11-22 | 2020-11-29 | bar: 1 to 8
| Creation/Update of Burn Down Chart | 6 days | Tom |  | 2020-11-24 | 2020-11-29 | bar: 3 to 7
| Group Meeting 1 | 1 day | All Members |  | 2020-11-24 | 2020-11-24 | bar: 3
| - Check on Tasks | 1 day | All Members |  | 2020-11-24 | 2020-11-24 | bar: 3
| - Review Work Done | 1 day | All Members |  | 2020-11-24 | 2020-11-24 | bar: 3
Sprint 2 |  |  |  |  | 2020-11-30 | 2020-12-19
| Update Initial Project Plan | 21 days | Tom |  | 2020-11-30 | 2020-12-19 | bar: 9 to 29
| Update Burn Down Chart | 21 days | Tom |  | 2020-11-30 | 2020-12-19 | bar: 9 to 29
| Update Gantt Chart | 21 days | Tom |  | 2020-11-30 | 2020-12-19 | bar: 9 to 29
| Creation of Servlets | 5 days | Mohammed |  | 2020-11-30 | 2020-12-03 | bar: 9 to 13
| Coding JDBC | 10 days | Tom, Yonis |  | 2020-11-30 | 2020-12-08 | bar: 9 to 27
| - Setting up Connection to Database. | 4 days | Tom, Yonis |  | 2020-11-30 | 2020-12-02 | bar: 9 to 12
| - Allow User to Insert / View Data | 6 days | Tom, Yonis |  | 2020-12-03 | 2020-12-08 | bar: 13 to 18
| Code Backend Architecture | 19 days | Yonis, Abdullah |  | 2020-11-30 | 2020-12-17 | bar: 9 to 27
| - Creating dashboards. | 5 days | Yonis, Abdullah |  | 2020-11-30 | 2020-11-03 | bar: 9 to 13
| - Creating login/registration pages for Members | 4 days | Yonis, Abdullah |  | 2020-12-04 | 2020-12-07 | bar: 14 to 17
| - Selecting Type of Users and Actions | 10 days | Yonis, Abdullah |  | 2020-11-08 | 2020-12-17 | bar: 18 to 27
| Code Underlying Program | 19 days | Mohammed, Joshua |  | 2020-11-30 | 2020-12-17 | bar: 9 to 27
| Update Task Delivery Form | 21 days | Joshua |  | 2020-11-30 | 2020-12-19 | bar: 9 to 29
| Group Meeting 2 | 1 day | All Members |  | 2020-12-08 | 2020-12-08 | bar: 9
| - Review Underlying Code | 1 day | All Members |  | 2020-12-08 | 2020-12-08 | bar: 9
| - Review Project Plan | 1 day | All Members |  | 2020-12-08 | 2020-12-08 | bar: 9
| - Review Backend Architecture | 1 day | All Members |  | 2020-12-08 | 2020-12-08 | bar: 9
| Group Meeting 3 | 1 day | All Members |  | 2020-12-18 | 2020-12-18 | bar: 28
| - Finalise Backend Architecture | 1 day | All Members |  | 2020-12-18 | 2020-12-18 | bar: 28
| - Finalise Project Plan | 1 day | All Members |  | 2020-12-18 | 2020-12-18 | bar: 28
| - Finalise Underlying Code | 1 day | All Members |  | 2020-12-18 | 2020-12-18 | bar: 28
| - Group Deliverables Together for Sprint 3 | 1 day | All Members |  | 2020-12-18 | 2020-12-18 | bar: 28
| - Discuss Final Changes for Sprint 3 | 1 day | All Members |  | 2020-12-18 | 2020-12-18 | bar: 28
Sprint 3 |  |  |  |  | 2021-01-06 | 2021-01-20 | bar: 30 to 44
| Update Final Changes | 6 days | All Members |  | 2021-01-06 | 2021-01-11 | bar: 30 to 35
| Finalise Gantt Chart | 13 days | Tom |  | 2021-01-06 | 2021-01-18 | bar: 30 to 42
| Finalise Burn Down Chart | 13 days | Tom |  | 2021-01-06 | 2021-01-18 | bar: 30 to 42
| Update / Finalise Task Delivery Form | 13 days | Joshua |  | 2021-01-06 | 2021-01-18 | bar: 30 to 42
| Test Cases | 8 days | Mohammed, Joshua, Yonis, Abdullah |  | 2021-01-11 | 2021-01-18 | bar: 35 to 42
| Finalise Project | 2 days | All Members |  | 2021-01-20 | 2021-01-21 | bar: 44 to 45
| Group Meeting 4 | 1 day | All Members |  | 2021-01-10 | 2021-01-10 | bar: 34
| - Review Deliverables for Final Deadline | 1 day | All Members |  | 2021-01-10 | 2021-01-10 | bar: 34
| Group Meeting 5 | 1 day | All Members |  | 2021-01-19 | 2021-01-19 | bar: 43
| - Collecting Deliverables Ready for Finalisation | 1 day | All Members |  | 2021-01-19 | 2021-01-19 | bar: 43
[5 empty] | Colour Key | Number Key
Sprints
|  |  |  | Sprint 1 |  | 1 to 8
|  |  |  | Sprint 2 |  | 9 to 29
|  |  |  | Sprint 3 |  | 30 to 45